## KTSumaary
Priority | Application | Module | Trainer | duration(hrs) | Team member | plan date | actual date | status
2 | IRGateway (distributor) | app architecture | puneet | 1 | promod ranjeet Rajesh shaadab | 2016-06-08 | 2016-06-10 | Completed
5 | IRGateway (RC/Syndicate) |  | puneet |  | promod ranjeet Rajesh shaadab |  |  | parked
4 | IRGateway (VC) |  | puneet |  | promod ranjeet Rajesh shaadab |  |  | parked
3 | CRM | CRM-Architecture | puneet | 1 | promod ranjeet Rajesh shaadab |  |  | In-Queque
1 | WMS | app architecture | prabhakar | 1 | Rajesh ranjeet Shadab | 2016-06-03 | 2016-06-07 | Completed
6 | Android App | Android architecture | Ankesh | 2 | Prabhakar Shadab |  |  | In-Queque
7 | IOS App | IOS architecture | Vivek | 2 | Prabhakar Shadab Ankesh |  |  | In-Queque
8 | Trainee KT | WMS (Overview) | prabhakar | 1 | Abhimanyu Singh | 2016-07-16 | 2016-07-16 | Completed
9 | Trainee KT | Development Overview | Pramod Kaira | 1 | Anmol Srivastva | 2016-07-20 | 2016-07-20 | Completed
10 | MLM | Table Structure for Calcuculation impact | Prabhakar Kumar | 1 | Rajesh Kr Shadabh Ah | 2016-07-21 | 2016-07-26 | In-Process

## KTPlan
Priority | Application | Module | Trainer | duration(hrs) | Team member | plan date | actual date | status | comments
2 | IRGateway (distributor) | app architecture | puneet | 1 | promod ranjeet Rajesh shaadab | 2016-06-08 | 2016-06-08 | Completed | IR Gateway Matc to be created
|  | Biz transaction | puneet | 2 | promod ranjeet Rajesh shaadab | 2016-06-08 | 2016-06-08 | Completed
|  | Reporting | puneet | 3 | promod ranjeet Rajesh shaadab | 2016-06-09 | 2016-06-09 | Completed
|  | code at a glance | puneet | 2 | promod ranjeet Rajesh shaadab | 2016-06-10 | 2016-06-10 | Completed
5 | IRGateway (RC/Syndicate) |  | puneet |  | promod ranjeet Rajesh shaadab |  |  | parked
4 | IRGateway (VC) |  | puneet |  | promod ranjeet Rajesh shaadab |  |  | parked
3 | CRM | CRM-Architecture | puneet | 1 | promod ranjeet Rajesh shaadab
|  | CRM-SCM | puneet | 2 | promod ranjeet Rajesh shaadab
|  | CRM-support | puneet | 3 | promod ranjeet Rajesh shaadab
|  | CRM-CC | puneet | 1 | promod ranjeet Rajesh shaadab
|  | CRM-CSS | puneet | 2 | promod ranjeet Rajesh shaadab
|  | CRM-Accounts | puneet | 2 | promod ranjeet Rajesh shaadab
|  | CRM-Sales | puneet | 1 | promod ranjeet Rajesh shaadab
|  | CRM-training | puneet | 1 | promod ranjeet Rajesh shaadab
|  | CRM - code at aglance | puneet | 1 | promod ranjeet Rajesh shaadab
1 | WMS | app architecture | prabhakar | 1 | Rajesh ranjeet Shadab | 2016-06-03 | 2016-06-03 | Completed
|  | Pre | prabhakar | 1 | Rajesh ranjeet Shadab | 2016-06-03 | 2016-06-03 | Completed
|  | inword | prabhakar | 2 | Rajesh ranjeet Shadab | 2016-06-04 | 2016-06-04 | Completed
|  | motherware house | prabhakar | 1 | Rajesh ranjeet Shadab | 2016-06-06 | 2016-06-06 | Completed
|  | production | prabhakar | 1 | Rajesh ranjeet Shadab | 2016-06-06 | 2016-06-06 | Completed
|  | dispatch | prabhakar | 1 | Rajesh ranjeet Shadab | 2016-06-07 | 2016-06-28 | Completed | Completed
|  | code at a glance | prabhakar | 1 | Rajesh ranjeet Shadab | 2016-06-07 | 2016-06-28 | Completed
6 | Android App | Android architecture | Ankesh | 2 | Prabhakar Shadab
|  | Galway App Flow | Ankesh | 2 | Prabhakar Shadab
|  | Galway App Code | Ankesh | 3 | Prabhakar Shadab
7 | IOS App | IOS architecture | Vivek | 2 | Prabhakar Shadab Ankesh
|  | Galway App Code | Vivek | 3 | Prabhakar Shadab Ankesh
8 | Trainee KT | WMS (Overview) | Prabhakar Kumar | 1 | Abhimanyu Singh | 2016-07-16 | 2016-07-16 | Completed
9 | Trainee KT | Development Overview | Pramod Kaira | 1 | Anmol Srivastva | 2016-07-20 | 2016-07-20 | In-Process
|  | Development Life Cycle | Pramod Kaira | 1 | Abhimanyu Singh Anmol S | 2016-07-21
|  |  |  | 1 | Abhimanyu Singh Anmol S | 2016-07-22
|  |  |  | 1 | Abhimanyu Singh Anmol S | 2016-07-25
|  | Business Logics | Rajkumar | 1 | Abhimanyu Singh Anmol S | 2016-07-26
10 | MLM | Table Structure for Calcuculation impact | Prabhakar Kumar | 1 | Rajesh Kr Shadabh Ah | 2016-07-21